## Sheet1
% Complete | Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names
0% | Auto Scheduled | <Customer> Lift Project | 20 days | Tue 10/4/22 | Mon 10/31/22
0% | Auto Scheduled | Initiation | 2 days | Tue 10/4/22 | Wed 10/5/22
0% | Auto Scheduled | Confirm Pre-requisites | 1 day | Tue 10/4/22 | Tue 10/4/22
0% | Auto Scheduled | Conduct Project Kick off meeting | 1 day | Wed 10/5/22 | Wed 10/5/22 | 3
0% | Auto Scheduled | Execution | 15 days | Tue 10/4/22 | Mon 10/24/22
0% | Auto Scheduled | Create OCI foundation | 13 days | Tue 10/4/22 | Thu 10/20/22
0% | Auto Scheduled | Base OCI Setup | 1 day | Thu 10/6/22 | Thu 10/6/22 | 4
0% | Auto Scheduled | VPN Setup | 2 days | Fri 10/7/22 | Mon 10/10/22 | 7
0% | Auto Scheduled | FastConnect Setup (Oracle) | 5 days | Fri 10/7/22 | Thu 10/13/22 | 7
0% | Auto Scheduled | FastConnect Setup (Customer) | 5 days | Fri 10/14/22 | Thu 10/20/22 | 9
0% | Auto Scheduled | Provisioning of DBCS | 1 day | Thu 10/6/22 | Thu 10/6/22 | 4
0% | Auto Scheduled | Enable CloudGuard | 1 day | Tue 10/4/22 | Tue 10/4/22
0% | Auto Scheduled | DB Migration Track - Non-Production and Production | 14 days | Tue 10/4/22 | Fri 10/21/22
0% | Auto Scheduled | Non-Production Export-Import | 4 days | Fri 10/7/22 | Wed 10/12/22
0% | Auto Scheduled | Perform backup @ source | 2 days | Fri 10/7/22 | Mon 10/10/22 | 11
0% | Auto Scheduled | Transfer backup to OCI | 1 day | Tue 10/11/22 | Tue 10/11/22 | 15
0% | Auto Scheduled | Restore backup to DBCS | 1 day | Wed 10/12/22 | Wed 10/12/22 | 16
0% | Auto Scheduled | Non-Production Final Export-Import | 4 days | Thu 10/13/22 | Tue 10/18/22
0% | Auto Scheduled | Perform backup @ source | 2 days | Thu 10/13/22 | Fri 10/14/22 | 17
0% | Auto Scheduled | Transfer backup to OCI | 1 day | Mon 10/17/22 | Mon 10/17/22 | 19
0% | Auto Scheduled | Restore backup to DBCS | 1 day | Tue 10/18/22 | Tue 10/18/22 | 20
0% | Auto Scheduled | Production Database Trial Run | 9 days | Tue 10/4/22 | Fri 10/14/22
0% | Auto Scheduled | Perform backup @ source | 2 days | Tue 10/4/22 | Wed 10/5/22
0% | Auto Scheduled | Transfer backup to OCI | 1 day | Thu 10/6/22 | Thu 10/6/22 | 23
0% | Auto Scheduled | Restore backup to DBCS | 1 day | Fri 10/7/22 | Fri 10/7/22 | 24
0% | Auto Scheduled | Test Production Integration | 5 days | Mon 10/10/22 | Fri 10/14/22 | 25
0% | Auto Scheduled | Cutover | 5 days | Mon 10/17/22 | Fri 10/21/22
0% | Auto Scheduled | Perform backup @ source | 2 days | Mon 10/17/22 | Tue 10/18/22 | 26
0% | Auto Scheduled | Transfer backup to OCI | 1 day | Wed 10/19/22 | Wed 10/19/22 | 28
0% | Auto Scheduled | Restore backup to DBCS | 1 day | Thu 10/20/22 | Thu 10/20/22 | 29
0% | Auto Scheduled | Cutover / Go-Live - Production Environment | 1 day | Fri 10/21/22 | Fri 10/21/22 | 30
0% | Auto Scheduled | DataSafe Enablement | 1 day | Tue 10/4/22 | Tue 10/4/22
0% | Auto Scheduled | Setup DataGuard | 1 day | Fri 10/21/22 | Fri 10/21/22 | 30
0% | Auto Scheduled | Solution Review | 1 day | Mon 10/24/22 | Mon 10/24/22 | 33
0% | Auto Scheduled | Platform Validation & Connectivity Testing | 5 days | Tue 10/4/22 | Mon 10/10/22
0% | Auto Scheduled | Support for Testing | 5 days | Tue 10/4/22 | Mon 10/10/22
0% | Auto Scheduled | Secure Implementation | 1 day | Tue 10/25/22 | Tue 10/25/22
0% | Auto Scheduled | Review Cloud Guard Status | 1 day | Tue 10/25/22 | Tue 10/25/22 | 34
0% | Auto Scheduled | Review Datasafe Status | 1 day | Tue 10/25/22 | Tue 10/25/22 | 34
0% | Auto Scheduled | Complete OSSA Checklist | 1 day | Tue 10/25/22 | Tue 10/25/22 | 34
0% | Auto Scheduled | Handover | 4 days | Wed 10/26/22 | Mon 10/31/22
0% | Auto Scheduled | Complete & Review Documentation | 2 days | Wed 10/26/22 | Thu 10/27/22 | 40
0% | Auto Scheduled | Handover & Review Meeting | 1 day | Fri 10/28/22 | Fri 10/28/22 | 42
0% | Auto Scheduled | Close Project | 1 day | Mon 10/31/22 | Mon 10/31/22 | 43