## Sheet1
% Work Complete | Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names
0% | Auto Scheduled | EXACC Project Plan | 31 days | Mon 1/23/23 | Mon 3/6/23
0% | Auto Scheduled | Initiation | 7 days | Mon 1/23/23 | Tue 1/31/23
0% | Auto Scheduled | Confirmation of prerequisites | 1 day | Mon 1/23/23 | Mon 1/23/23
0% | Auto Scheduled | Access to tenancy & on-premises | 1 day | Tue 1/24/23 | Tue 1/24/23 | 3
0% | Auto Scheduled | DB Details Validation | 1 day | Wed 1/25/23 | Wed 1/25/23 | 4
0% | Auto Scheduled | EXACC Hardware Readiness | 3 days | Thu 1/26/23 | Mon 1/30/23 | 5
0% | Auto Scheduled | Kickoff Project | 1 day | Tue 1/31/23 | Tue 1/31/23 | 6
0% | Auto Scheduled | Execution | 24 days | Wed 2/1/23 | Mon 3/6/23
0% | Auto Scheduled | Infrastructure | 8 days | Wed 2/1/23 | Fri 2/10/23
0% | Auto Scheduled | Setup OCI Foundation | 2 days | Wed 2/1/23 | Thu 2/2/23 | 7
0% | Auto Scheduled | Setup of Networking | 2 days | Fri 2/3/23 | Mon 2/6/23 | 10
0% | Auto Scheduled | Setup EXACC Cluster | 2 days | Tue 2/7/23 | Wed 2/8/23 | 11
0% | Auto Scheduled | Setup Oracle Homes | 2 days | Thu 2/9/23 | Fri 2/10/23 | 12
0% | Auto Scheduled | Database Migration Non-Production | 10 days | Mon 2/13/23 | Fri 2/24/23
0% | Auto Scheduled | DB Migration Readiness - on-premises | 5 days | Mon 2/13/23 | Fri 2/17/23 | 13
0% | Auto Scheduled | Provision of Database Home as CDB | 5 days | Mon 2/20/23 | Fri 2/24/23 | 15
0% | Auto Scheduled | Source DB Export | 5 days | Mon 2/20/23 | Fri 2/24/23 | 15
0% | Auto Scheduled | Transfer export backup to OCI | 5 days | Mon 2/20/23 | Fri 2/24/23 | 15
0% | Auto Scheduled | Database import | 5 days | Mon 2/20/23 | Fri 2/24/23 | 15
0% | Auto Scheduled | Application Testing and Validation | 5 days | Mon 2/20/23 | Fri 2/24/23 | 15
0% | Auto Scheduled | Database Migration Production | 6 days | Mon 2/27/23 | Mon 3/6/23
0% | Auto Scheduled | DB Migration Readiness - on-premises | 1 day | Mon 2/27/23 | Mon 2/27/23 | 19
0% | Auto Scheduled | Provision of Database Home as CDB | 1 day | Tue 2/28/23 | Tue 2/28/23 | 22
0% | Auto Scheduled | Source DB Export | 1 day | Wed 3/1/23 | Wed 3/1/23 | 23
0% | Auto Scheduled | Transfer export backup to OCI | 1 day | Thu 3/2/23 | Thu 3/2/23 | 24
0% | Auto Scheduled | Database import | 1 day | Fri 3/3/23 | Fri 3/3/23 | 25
0% | Auto Scheduled | Application Testing and Validation | 1 day | Tue 2/28/23 | Tue 2/28/23 | 22
0% | Auto Scheduled | Cutover | 1 day | Mon 3/6/23 | Mon 3/6/23 | 28
0% | Auto Scheduled | DR Setup (If Scoped) | 4 days | Mon 2/27/23 | Thu 3/2/23
0% | Auto Scheduled | Provision of Database Home as CDB | 1 day | Mon 2/27/23 | Mon 2/27/23 | 19
0% | Auto Scheduled | Setup Dataguard | 1 day | Tue 2/28/23 | Tue 2/28/23 | 30
0% | Auto Scheduled | Validate Replicated DB | 1 day | Wed 3/1/23 | Wed 3/1/23 | 31
0% | Auto Scheduled | Knowledge Transfer | 1 day | Thu 3/2/23 | Thu 3/2/23 | 28,32
0% | Auto Scheduled | OSSA Activities | 1 day | Thu 3/2/23 | Thu 3/2/23 | 13,32
0% | Auto Scheduled | Documentation | 1 day | Thu 3/2/23 | Thu 3/2/23 | 13,32
0% | Auto Scheduled | Handover | 1 day | Fri 3/3/23 | Fri 3/3/23 | 35