## Plan
% Complete | Task Mode | Task Name | Duration | Start | Finish | Actual Finish | Predecessors | Resource Names
0% | Auto Scheduled | <Customer> ExaCS Project | 76 days | Mon 9/5/22 | Mon 12/19/22 | NA
0% | Auto Scheduled | Initiation | 1 day | Mon 9/5/22 | Mon 9/5/22 | NA
0% | Auto Scheduled | Validate Pre-Requisites | 1 day | Mon 9/5/22 | Mon 9/5/22 | NA
0% | Auto Scheduled | Project Kickoff | 1 day | Mon 9/5/22 | Mon 9/5/22 | NA
0% | Auto Scheduled | Execution | 75 days | Tue 9/6/22 | Mon 12/19/22 | NA
0% | Auto Scheduled | Core OCI Workload | 10 days | Tue 9/6/22 | Mon 9/19/22 | NA
0% | Auto Scheduled | OCI Foundation | 1 day | Tue 9/6/22 | Tue 9/6/22 | NA | 4
0% | Auto Scheduled | Provision ExaCS | 3 days | Wed 9/7/22 | Fri 9/9/22 | NA | 7
0% | Auto Scheduled | Provision VM Cluster in Primary | 5 days | Mon 9/12/22 | Fri 9/16/22 | NA | 8
0% | Auto Scheduled | Provision VM Cluster in DR (If Scoped) | 0 days | Fri 9/16/22 | Fri 9/16/22 | NA | 9
0% | Auto Scheduled | Oracle Home Deployment | 1 day | Mon 9/19/22 | Mon 9/19/22 | NA | 10
0% | Auto Scheduled | Database Workload | 65 days | Tue 9/20/22 | Mon 12/19/22 | NA
0% | Auto Scheduled | DB Migration - Trial Run | 25 days | Tue 9/20/22 | Mon 10/24/22 | NA
0% | Auto Scheduled | Export Source DB and Copy to OCI | 25 days | Tue 9/20/22 | Mon 10/24/22 | NA | 11
0% | Auto Scheduled | Import Source DB to ExaCS | 25 days | Tue 9/20/22 | Mon 10/24/22 | NA | 11
0% | Auto Scheduled | DB Validations | 25 days | Tue 9/20/22 | Mon 10/24/22 | NA | 11
0% | Auto Scheduled | DataGuard Setup and Configuration | 15 days | Tue 10/25/22 | Mon 11/14/22 | NA | 16
0% | Auto Scheduled | DB Migration Production - Final Run | 15 days | Tue 11/15/22 | Mon 12/5/22 | NA
0% | Auto Scheduled | Export Source DB and Copy to OCI | 15 days | Tue 11/15/22 | Mon 12/5/22 | NA | 17
0% | Auto Scheduled | Import Source DB to ExaCS | 15 days | Tue 11/15/22 | Mon 12/5/22 | NA | 17
0% | Auto Scheduled | DB Validations | 15 days | Tue 11/15/22 | Mon 12/5/22 | NA | 17
0% | Auto Scheduled | Go-Live / Cutover | 15 days | Tue 11/15/22 | Mon 12/5/22 | NA | 17
0% | Auto Scheduled | Platform Validation and Testing | 10 days | Tue 12/6/22 | Mon 12/19/22 | NA | 22
0% | Auto Scheduled | Support for Testing | 10 days | Tue 12/6/22 | Mon 12/19/22 | NA | 22
0% | Auto Scheduled | Secure Implementation | 2 days | Tue 12/6/22 | Wed 12/7/22 | NA
0% | Auto Scheduled | Cloud Guard Review | 1 day | Tue 12/6/22 | Tue 12/6/22 | NA | 22
0% | Auto Scheduled | Solution Review | 1 day | Wed 12/7/22 | Wed 12/7/22 | NA | 26
0% | Auto Scheduled | Data Safe Enablement | 1 day | Wed 12/7/22 | Wed 12/7/22 | NA | 26
0% | Auto Scheduled | Closure | 3 days | Thu 12/8/22 | Mon 12/12/22 | NA
0% | Auto Scheduled | Documentation Updates | 2 days | Thu 12/8/22 | Fri 12/9/22 | NA | 28
0% | Auto Scheduled | Handover Project | 1 day | Mon 12/12/22 | Mon 12/12/22 | NA | 30