## XTTS Project Plan
% Complete | Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names
0% | Auto Scheduled | <Customer> Lift Project | 37 days | Tue 10/4/22 | Wed 11/23/22
0% | Auto Scheduled | Initiation | 2 days | Tue 10/4/22 | Wed 10/5/22
0% | Auto Scheduled | Confirm Pre-requisites | 1 day | Tue 10/4/22 | Tue 10/4/22
0% | Auto Scheduled | Conduct Project Kick off meeting | 1 day | Wed 10/5/22 | Wed 10/5/22 | 3
0% | Auto Scheduled | Execution | 34 days | Thu 10/6/22 | Tue 11/22/22
0% | Auto Scheduled | Create OCI foundation | 11 days | Thu 10/6/22 | Thu 10/20/22
0% | Auto Scheduled | Base OCI Setup | 1 day | Thu 10/6/22 | Thu 10/6/22 | 4
0% | Auto Scheduled | VPN Setup | 2 days | Fri 10/7/22 | Mon 10/10/22 | 7
0% | Auto Scheduled | FastConnect Setup (Oracle) | 5 days | Fri 10/7/22 | Thu 10/13/22 | 7
0% | Auto Scheduled | FastConnect Setup (Customer) | 5 days | Fri 10/14/22 | Thu 10/20/22 | 9
0% | Auto Scheduled | DBCS Provisioning | 2 days | Thu 10/6/22 | Fri 10/7/22 | 4
0% | Auto Scheduled | Setup WAF / LB ( If Scoped ) | 2 days | Thu 10/6/22 | Fri 10/7/22 | 4
0% | Auto Scheduled | Enable CloudGuard | 1 day | Mon 10/10/22 | Mon 10/10/22 | 12
0% | Auto Scheduled | DB Migration Track (Add environments based on scope) | 26 days | Mon 10/10/22 | Mon 11/14/22
0% | Auto Scheduled | L0 Backup | 6 days | Mon 10/10/22 | Mon 10/17/22
0% | Auto Scheduled | Perform Full Backup @ Source | 2 days | Mon 10/10/22 | Tue 10/11/22 | 12
0% | Auto Scheduled | Transfer Backup to OCI | 2 days | Wed 10/12/22 | Thu 10/13/22 | 16
0% | Auto Scheduled | Restore Backup to DBCS | 2 days | Fri 10/14/22 | Mon 10/17/22 | 17
0% | Auto Scheduled | L1 Incremental Backup | 6 days | Tue 10/18/22 | Tue 10/25/22
0% | Auto Scheduled | Perform Incremental Backup @ Source | 2 days | Tue 10/18/22 | Wed 10/19/22 | 18
0% | Auto Scheduled | Transfer Backup to OCI | 2 days | Thu 10/20/22 | Fri 10/21/22 | 20
0% | Auto Scheduled | Restore Backup to DBCS | 2 days | Mon 10/24/22 | Tue 10/25/22 | 21
0% | Auto Scheduled | Production Database Trial Run | 8 days | Wed 10/26/22 | Fri 11/4/22
0% | Auto Scheduled | Final Database and Metadata Backup @ Source | 2 days | Wed 10/26/22 | Thu 10/27/22 | 22
0% | Auto Scheduled | Transfer Backup to OCI | 2 days | Fri 10/28/22 | Mon 10/31/22 | 24
0% | Auto Scheduled | Restore Backup to DBCS | 2 days | Tue 11/1/22 | Wed 11/2/22 | 25
0% | Auto Scheduled | Test Production Integration | 2 days | Thu 11/3/22 | Fri 11/4/22 | 26
0% | Auto Scheduled | Cutover | 6 days | Mon 11/7/22 | Mon 11/14/22
0% | Auto Scheduled | Final DB & Metadata Backup @ Source | 2 days | Mon 11/7/22 | Tue 11/8/22 | 27
0% | Auto Scheduled | Export Backup to OCI | 2 days | Wed 11/9/22 | Thu 11/10/22 | 29
0% | Auto Scheduled | Restore Backup to DBCS | 2 days | Fri 11/11/22 | Mon 11/14/22 | 30
0% | Auto Scheduled | Setup & Configure DataGuard | 2 days | Thu 11/3/22 | Fri 11/4/22 | 26
0% | Auto Scheduled | DataSafe Enablement | 1 day | Mon 11/7/22 | Mon 11/7/22 | 32
0 | Auto Scheduled | Cutover / GoLive - Production Environment | 1 day | Tue 11/15/22 | Tue 11/15/22 | 31
0% | Auto Scheduled | Solution Review | 1 day | Wed 11/16/22 | Wed 11/16/22 | 34
0% | Auto Scheduled | Platform Validation & Connectivity Testing | 5 days | Wed 11/16/22 | Tue 11/22/22 | 34
0% | Auto Scheduled | Support for Testing | 5 days | Wed 11/16/22 | Tue 11/22/22 | 34
0% | Auto Scheduled | Secure Implementation | 1 day | Thu 11/17/22 | Thu 11/17/22
0% | Auto Scheduled | Review Cloud Guard Status | 1 day | Thu 11/17/22 | Thu 11/17/22 | 35
0% | Auto Scheduled | Review DataSafe Status | 1 day | Thu 11/17/22 | Thu 11/17/22 | 35
0% | Auto Scheduled | Complete OSSA Checklist | 1 day | Thu 11/17/22 | Thu 11/17/22 | 35
0% | Auto Scheduled | Handover | 4 days | Fri 11/18/22 | Wed 11/23/22
0% | Auto Scheduled | Complete & Review Documentation | 2 days | Fri 11/18/22 | Mon 11/21/22 | 41
0% | Auto Scheduled | Handover & Review Meeting | 1 day | Tue 11/22/22 | Tue 11/22/22 | 43
0% | Auto Scheduled | Close Project | 1 day | Wed 11/23/22 | Wed 11/23/22 | 44