## VM Migration
% Complete | Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names
0% | Auto Scheduled | Customer Lift Project | 70 days | Tue 10/4/22 | Mon 1/9/23
0% | Auto Scheduled | Initiation | 2 days | Tue 10/4/22 | Wed 10/5/22
0% | Auto Scheduled | Confirm Pre-requisites | 1 day | Tue 10/4/22 | Tue 10/4/22
0% | Auto Scheduled | Conduct Project Kick off meeting | 1 day | Wed 10/5/22 | Wed 10/5/22 | 3
0% | Auto Scheduled | Execution | 70 days | Tue 10/4/22 | Mon 1/9/23
0% | Auto Scheduled | Create OCI foundation | 13 days | Tue 10/4/22 | Thu 10/20/22
0% | Auto Scheduled | OCI Base Configuration | 1 day | Thu 10/6/22 | Thu 10/6/22 | 4
0% | Auto Scheduled | VPN Setup | 1 day | Fri 10/7/22 | Fri 10/7/22 | 7
0% | Auto Scheduled | FastConnect Setup (Customer) | 5 days | Fri 10/7/22 | Thu 10/13/22 | 7
0% | Auto Scheduled | FastConnect Setup (Oracle) | 5 days | Fri 10/14/22 | Thu 10/20/22 | 9
0% | Auto Scheduled | Setup Load Balancer and WAF ( If Scoped ) | 1 day | Thu 10/6/22 | Thu 10/6/22 | 4
0% | Auto Scheduled | Enable CloudGuard | 1 day | Tue 10/4/22 | Tue 10/4/22
0% | Auto Scheduled | Rackware Migration Track | 67 days | Fri 10/7/22 | Mon 1/9/23
0% | Auto Scheduled | Rackware Server Setup & Configuration - OCI | 2 days | Fri 10/7/22 | Mon 10/10/22 | 11
0% | Auto Scheduled | Agent Installation on Source Servers - Customer | 5 days | Tue 10/11/22 | Mon 10/17/22 | 14
0% | Auto Scheduled | Connectivity Check on Source Servers | 1 day | Tue 10/18/22 | Wed 11/23/22 | 15
0% | Auto Scheduled | Migration of VMs | 10 days | Wed 11/23/22 | Mon 1/9/23 | 16
0% | Auto Scheduled | Sanity Check of VMs | 10 days | Wed 11/23/22 | Wed 12/7/22 | 16
0 | Auto Scheduled | Cutover / Go-Live - Production Environment | 1 day | Tue 10/4/22 | Tue 10/4/22
0% | Auto Scheduled | Solution Review | 1 day | Wed 10/5/22 | Wed 10/5/22 | 19
0% | Auto Scheduled | Platform Validation & Connectivity Testing | 5 days | Tue 10/4/22 | Mon 10/10/22
0% | Auto Scheduled | Support for Testing | 5 days | Tue 10/4/22 | Mon 10/10/22
0% | Auto Scheduled | Secure Implementation | 1 day | Thu 10/6/22 | Thu 10/6/22
0% | Auto Scheduled | Review Cloud Guard Status | 1 day | Thu 10/6/22 | Thu 10/6/22 | 20
0% | Auto Scheduled | Complete OSSA Checklist | 1 day | Thu 10/6/22 | Thu 10/6/22 | 20
0% | Auto Scheduled | Handover | 4 days | Fri 10/7/22 | Wed 10/12/22
0% | Auto Scheduled | Review Documentation | 2 days | Fri 10/7/22 | Mon 10/10/22 | 26
0% | Auto Scheduled | Handover | 1 day | Tue 10/11/22 | Tue 10/11/22 | 28
0% | Auto Scheduled | Close Project | 1 day | Wed 10/12/22 | Wed 10/12/22 | 29