## ZDM
% Complete | Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Actual Finish
0% | Auto Scheduled | Customer Project | 44 days | Tue 11/22/22 | Fri 1/20/23 |  |  | NA
0% | Auto Scheduled | Initiation | 5 days | Tue 11/22/22 | Mon 11/28/22 |  |  | NA
0% | Auto Scheduled | Confirm pre-requisites | 4 days | Tue 11/22/22 | Fri 11/25/22 |  |  | NA
0% | Auto Scheduled | Project Kickoff | 0 days | Fri 11/25/22 | Fri 11/25/22 | 3 |  | NA
0% | Auto Scheduled | Define & Analyze Migration Approach | 1 day | Mon 11/28/22 | Mon 11/28/22 | 4 |  | NA
0% | Auto Scheduled | Review & Acceptance of Approach | 0 days | Mon 11/28/22 | Mon 11/28/22 | 5 |  | NA
0% | Auto Scheduled | DB Migration Planning | 3 days | Tue 11/29/22 | Thu 12/1/22 |  |  | NA
0% | Auto Scheduled | DB Discovery & ZDM pre-requisite Setup | 0.5 days | Tue 11/29/22 | Tue 11/29/22 | 6 |  | NA
0% | Auto Scheduled | ZDM & Database Health Check | 0.5 days | Tue 11/29/22 | Tue 11/29/22 | 8 |  | NA
0% | Auto Scheduled | Network & Port Configuration for ZDM | 1 day | Wed 11/30/22 | Wed 11/30/22 | 9 |  | NA
0% | Auto Scheduled | ZDM Setup & Configuration | 0.5 days | Thu 12/1/22 | Thu 12/1/22 | 10 |  | NA
0% | Auto Scheduled | Local Storage Setup & Configuration | 0.5 days | Thu 12/1/22 | Thu 12/1/22 | 11 |  | NA
0% | Auto Scheduled | DB Migration ZDM - Non Production | 11 days | Fri 12/2/22 | Fri 12/16/22 |  |  | NA
0% | Auto Scheduled | ZDM Evaluation and Pre-migration Execution | 2 days | Fri 12/2/22 | Mon 12/5/22 | 12 |  | NA
0% | Auto Scheduled | Remediate Issues | 2 days | Tue 12/6/22 | Wed 12/7/22 | 14 |  | NA
0% | Auto Scheduled | Execute Migration Job | 5 days | Thu 12/8/22 | Wed 12/14/22 | 15 |  | NA
0% | Auto Scheduled | Post Migration Basic Sanity Check | 2 days | Thu 12/15/22 | Fri 12/16/22 | 16 |  | NA
0% | Auto Scheduled | DB Migration ZDM - Production Trial Run | 11 days | Mon 12/19/22 | Mon 1/2/23 |  |  | NA
0% | Auto Scheduled | ZDM Evaluation & Pre-migration Execution | 2 days | Mon 12/19/22 | Tue 12/20/22 | 17 |  | NA
0% | Auto Scheduled | Remediate Issues | 2 days | Wed 12/21/22 | Thu 12/22/22 | 19 |  | NA
0% | Auto Scheduled | Execute Migration Job | 5 days | Fri 12/23/22 | Thu 12/29/22 | 20 |  | NA
0% | Auto Scheduled | Post Migration Basic Sanity Check | 2 days | Fri 12/30/22 | Mon 1/2/23 | 21 |  | NA
0% | Auto Scheduled | DB Migration ZDM - Production Go-Live | 11 days | Tue 1/3/23 | Tue 1/17/23 |  |  | NA
0% | Auto Scheduled | ZDM Evaluation & Premigration Execution | 2 days | Tue 1/3/23 | Wed 1/4/23 | 22 |  | NA
0% | Auto Scheduled | Remediate Issues | 2 days | Thu 1/5/23 | Fri 1/6/23 | 24 |  | NA
0% | Auto Scheduled | Execute Migration Job | 5 days | Mon 1/9/23 | Fri 1/13/23 | 25 |  | NA
0% | Auto Scheduled | Post Migration Basic Sanity Check | 2 days | Mon 1/16/23 | Tue 1/17/23 | 26 |  | NA
0% | Auto Scheduled | Application Testing & Validation | 20 days | Thu 12/15/22 | Wed 1/11/23 | 16 |  | NA
0% | Auto Scheduled | DataSafe Setup | 2 days | Mon 1/16/23 | Tue 1/17/23 | 26 |  | NA
0% | Auto Scheduled | Project Documentation | 2 days | Wed 1/18/23 | Thu 1/19/23 | 29 |  | NA
0% | Auto Scheduled | Project Handover | 1 day | Fri 1/20/23 | Fri 1/20/23 | 30 |  | NA